## MVP TODO
Phase | Area | Task | Type | Priority | Status | Owner | Due Date | Notes
Phase 1 – Foundation | Security & config | Remove hardcoded Google Maps API key; use option or constant.
Phase 1 – Foundation | Security & config | Remove hardcoded reCAPTCHA secret; use option or constant.
Phase 1 – Foundation | Security & config | Ensure all AJAX handlers use nonce + sanitize + consistent JSON response shape.
Phase 1 – Foundation | Shared shell & UX | Navigation (desktop + mobile): layout and tap targets.
Phase 1 – Foundation | Shared shell & UX | Toast, popup, loader: work on all endpoints and on small viewports.
Phase 1 – Foundation | Shared shell & UX | Responsive: nav collapse/expand on mobile; content full-width on small screens. | Responsive
Phase 2 – Orders & View Order | Orders endpoint | Order list: status, date, total, empty state.
Phase 2 – Orders & View Order | Orders endpoint | Pagination works; no layout break on small screens.
Phase 2 – Orders & View Order | Orders endpoint | Responsive: list/cards readable at 320px; table → stacked cards or scroll if kept. | Responsive
Phase 2 – Orders & View Order | View-order endpoint | Order details: items, totals, addresses, status.
Phase 2 – Orders & View Order | View-order endpoint | Actions (pay/cancel/reorder) if applicable.
Phase 2 – Orders & View Order | View-order endpoint | Responsive: details readable; CTAs not clipped; no horizontal scroll. | Responsive
Phase 3 – Self-service | Address Book | List/add/edit/delete; default address sync to Woo shipping.
Phase 3 – Self-service | Address Book | Server-side validation and address_book schema/limits.
Phase 3 – Self-service | Address Book | Responsive: form single column on mobile; primary CTA above fold. | Responsive
Phase 3 – Self-service | Edit Account | Profile (name, email) + change password in one flow.
Phase 3 – Self-service | Edit Account | Validation and error display.
Phase 3 – Self-service | Edit Account | Responsive: form fields full-width; submit button visible without scroll on 320px. | Responsive
Phase 4 – Completion & release | Payment methods | List saved methods; add/remove (per gateway).
Phase 4 – Completion & release | Payment methods | Responsive: list and add flow usable on mobile. | Responsive
Phase 4 – Completion & release | Auth | Login, signup, lost-password, reset-password: flows work and errors clear.
Phase 4 – Completion & release | Auth | Responsive: auth forms usable on 320px; no overflow. | Responsive
Phase 4 – Completion & release | Release QA | Smoke test all endpoints logged-in and logged-out.
Phase 4 – Completion & release | Release QA | Responsive pass: 320px, 768px, 1280px for each endpoint. | Responsive
Phase 4 – Completion & release | Release QA | Ownership mode switch (plugin/theme) does not break My Account.